## Slide 1: Software Project Management
Lecture 08
Time Management
Lecture 8:
Software Project Planning: Time Management

## Slide 2: Project Time Estimates
What do we need, in order to estimate project time?

## Slide 3: Project Time Estimates
Gather Requirements
Create a WBS
Determine Skill Sets & Resources

## Slide 4: Project Time Estimates
Gather Requirements
Create a WBS
Determine Skill Sets & Resources
NOTE: The more details you have, the better prepared you’ll be to factor in delays, risks, and small time-consuming jobs.

## Slide 5: Project Time Estimates
Gather Requirements
Create a WBS
Determine Skill Sets & Resources
NOTE: Use “Progressive Elaboration” when you’re developing a project schedule. At the start of the project, you create the schedule based on the requirements that you’ve gathered, but as you gain more detailed knowledge of the project specifications, you fine-tune the schedule and make it more comprehensive.

## Slide 6: Project Time Estimates
Gather Requirements
Create a WBS
Determine Skill Sets & Resources
NOTE: You need the work breakdown structure (WBS) and the activity list that comes from the WBS. The information in the WBS tells you what activities have to happen.

## Slide 7: Project Time Estimates
Gather Requirements
Create a WBS
Determine Skill Sets & Resources
NOTE: Your project team members are closest to the project work, so they understand what the project work entails. You need them to help you make the best decisions about which activities should happen in which order - and how long these activities might take.

## Slide 8: Project Network Diagram
Project Network Diagram (PND) is a roadmap of the sequence of activities needed to complete the project work
A picture showing the chronological relationships among the work packages
The relationship among work packages is called the predecessor and successor relationships
“Predecessor” refers to a work package that must be performed before another work package can be started. “Successor” work package refers to a work package that must be started after a previous one is completed.
“Network diagram” is a generic name; the names “precedent diagram” and “activity on the node (AON) diagram” are also names used for this picture.

## Slide 9: Project Network Diagram

## Slide 10: Project Network Diagram
Identify the order in which the work should, or can, happen
Make educated decisions about the order of the activities that may influence project timings, forecasting, and labor assignments.
You will discover that some tasks are more complicated than others, you can assign these activities to more experienced team members
Some activities are effort-driven, which means that you can add more labor to complete the work faster.
Some activities are of fixed duration, which means they’ll take the same amount of time regardless of how many people you put on them.

## Slide 11: Activities in PND
First Activity: Start
Last Activity: Finish
Predecessor: Activities that precede the downstream activities
Successor: Activities that come after predecessor activities

## Slide 12: Activity Sequencing
A dependency or relationship relates to the sequencing of project tasks.
Does a certain activity have to be finished before another one can start?
Can the project team do several activities in parallel?
Can some overlap?
Determining these relationships or dependencies between activities has a significant impact on developing and managing a project schedule

## Slide 13: Activity Relationships
The relationship between activities describes when activities begin and end.
A finish-to-start relationship exists if one activity must finish before another activity starts.
A start-to-start relationship exists if one activity cannot start until another activity starts.
A finish-to-finish relationship exists if the one activity cannot finish until another activity finishes.
Finally, a start-to-finish relationship exists if one activity must start before another can finish.

## Slide 14: 1. Finish-to-start (FS):
The finish-to-start is the most common relationship but you must use the relationship required by the logic connecting the two adjacent work packages.
For example, work package 4.8, “Shingle the Roof,” must follow work package 4.1, “Build House Frame.” Therefore the relationship between work package 4.8 and work package 4.1 must be a finish-to-start with 4.8 the successor.

## Slide 15: 2. Finish-to-finish:
Sometimes two work packages must finish on the same day.
For example, we have a construction project in a remote area.
“Deliver Materials” is work package C and “Deliver Workers” is work package D.
These two work packages will take different amounts of time to complete but both must be completed on the same day.
A finish-to-finish relationship would seem appropriate between work packages C and D

## Slide 16: 3. Start-to-start:
Sometimes two work packages can start on the same day.
Such is the case for work package 5.1 “Install Rough Wiring” and 6.1 “Install Rough Plumbing.
” A start-to-start relationship would seem appropriate between work package 5.1 and work package 6.1 because the schedule planners want them both to start on the same day

## Slide 17: 4. Start-to-finish:
The predecessor activity must start in order for the successor activity to finish.
This is the most unusual of all the relationship types and is rarely used.
Example: The software testing can’t be completed until the quality control department starts reviews the testing results

## Slide 18: Determining Project Dependencies
Identify dependencies that will influence how you sequence various activities.
According to PMBOK, there are four types of project dependencies that you need to consider
  Mandatory
  Discretionary
  External
  Internal

## Slide 19: Using Hard Logic (Mandatory Dependencies)
Hard logic describes the work that must be done in a particular order.
Mandatory Project Dependencies are those that are legally or contractually required. They are, sometimes, inherent in the nature of the work. Mandatory Project Dependencies are also called Hard Logic.
Consider 2 activities A and B. B has a Mandatory Dependency on A. It means action on B cannot be performed until Action on A has been completed. Let us look at following examples to understand:
A – Requirements Documentation; B – Client Approval
A – Lay Building Foundation; B – Construct Floor
A – Build Car Prototype; B – Perform Crash Testing

## Slide 20: Using Soft Logic (Discretionary Dependencies)
You use soft logic, sometimes called evaluating discretionary dependencies, when you make choices to arrange activities in a particular order not because you have to, but because you and the project team feel it’s the best order of the work.
Discretionary Project Dependencies are defined by the Project Team
There could be more than one way to define the sequence between 2 activities. The preference of the Project Team may be because of best practices or lessons learned from prior experiences. Discretionary Project Dependencies are also called Preferred Logic, Preferential Logic or Soft Logic.

## Slide 21: Using Soft Logic (Discretionary Dependencies)
Consider 2 activities A and B. B has a Discretionary dependency on A. It means action on B can be before Action on A has been completed. It can also mean that action on A and B can be independently performed. However, the Project Team has chosen to make B dependent on A. Let us look at following examples to understand:
A – Develop System Module X; B – Develop System Module Y
A – Furnish Room R; B – Furnish Room S
A – Book Airline Ticket; B – Buy Insurance

## Slide 22: External Dependencies
Many projects depend on vendors or other projects to move forward. These are referred to generally as external dependencies, and are typically out of the project manager’s control.
You should identify subprojects or outsourced portions of your project. These other projects are identified as subnets / fragnets and are often visualized in the network diagram as a cloud that shows the predecessor activities and successor activities of the subnet.

## Slide 23: External Dependencies
External Project Dependencies are defined between non-project Activities and project activities. The non-project activities are done by people who are external to the Project Team. It means people are not part of the Project Team e.g. Client, Vendor or any other external group. The project activities, on the other hand, are done by the Project Team. The Project Team usually does not have control over non-project activities.
Consider 2 activities A and B. B has an External Dependency on A. It means B is a project activity while A is a non-project activity. Following examples will be helpful in understanding:
A – Delivery of Equipment; B – Start Development
A – Approval of Building Plans; B – Start Construction

## Slide 24: Internal Dependencies
Internal Project Dependencies are defined between two project activities. The Project Team, usually, has complete control over project activities.
Consider 2 activities A and B. B has an Internal Dependency on A. It means both A and B are project activities. These are performed by the Project Team members. There is no involvement of any external party. Let us look at following examples to understand:
A – Develop System; B – Test System
A – Construct Wall; B – Paint Wall
A – Assemble Machine; B -Pack Machine

## Slide 25: Activity Duration Influencers
Activity duration influencers are any conditions that may cause the duration estimates you provide to be inaccurate, unstable, or subject to change.

## Slide 26: Activity Duration Influencers
Identifying Activity Duration Influencers / Risks
Project Assumptions Project assumptions include anything that you believe to be true, but that you can’t prove to be true. Hardware or Software conflicts won’t exist, team will deliver as scheduled, needed resources will be available, etc
Project Constraints A constraint is anything that may restrict the project manager’s ability to get the project done. Budget, Regulations, Organizational, Technical, Resources, etc
Resources & Capabilities If 8 developers can finish a project in four months doesn’t necessarily mean that you can add 16 developers to complete the job in half the time
First-Time, First-Use Penalty

## Slide 27: Project Time Estimates
What if you have to provide time estimates without enough “details in hand” or “time to analyze”?

## Slide 28: Project Time Estimates
Rough Order of Magnitude Estimate
Analogous Estimate
Parametric Estimate

## Slide 29: Rough Order of Magnitude
A ROM estimate can be wildly off target - from -25% to +75% percent off, or even more
Always preface ROM estimates with a disclaimer. For Example: “This is a wild estimate and I would need to gather more definitive project requirements in order to give you a more reliable estimate”

## Slide 30: Analogous Estimate
An analogous estimate is an estimate that creates an analogy between your proposed project and one that’s been done in the past.

## Slide 31: Parametric Estimate
A parametric estimate is one of the simplest estimates to offer but you may not have many opportunities to employ it in software project management.
For Example: A task may take 8 hours to complete; Project requires you to complete 10 similar task, than your estimate would be 80 hours.

## Slide 32: What To Say
What to say if your boss wants an estimate now:
  Clarify that this is only an estimate
  List your assumptions
  Offer a range of variance
  State the length of validity for the estimate
  Provide some background on how the estimate was created

## Slide 33: Do’s and Don’ts
Don’t Work Alone - Work with your project team to examine your project network diagram, determine the duration of each activity, and then determine when the project will be able to complete.
Don’t Guess - Time estimates must be as accurate as possible.
Don’t Bloat - Remember Parkinson’s Law states that work will expand to fill the amount of time allotted to it.(also called students’ syndrome)
Do Take Advantage of Management Reserve - Management reserve is a collection of time that’s appended to the end of your network diagram. (Usually 15%)

## Slide 34: Three-point Estimates
Three different estimates:
Minimum
Maximum
Mode
Mode: is the value that appears most often in a set of data.
You may also see/use:
Optimistic: The best-case scenario
Pessimistic: The worst that can happen
Most likely: The most-likely time

## Slide 35: Accurate Estimates
Two techniques that can be use to create more accurate estimates.
PERT Distribution: PERT means program evaluation and review technique
Triangular Distribution

## Slide 36: PERT Distribution
PERT Distribution formula:
    Maximum + Minimum + (4 x Mode)
    Then divide the sum by 6
    Max + Min + (4 x Mode) = 60 + 15 + (4 x 25) = 29 Hours
    6 6

## Slide 37: Triangular Distribution
Triangular Distribution formula:
    Maximum + Minimum + Mode
    Then divide the sum by 3
    Max + Min + Mode = 60 + 15 + 25 = 33 Hours
    3 3

## Slide 38: Rationale behind:
A three point estimate is a better estimate, compared to a single point estimate. Single point estimate simply gives you a single number
    Manager: How long will it take to complete the engine design?
    Engineer: 5 days
    The problem with single point estimates is that they are seldom correct
How reliable is this 5 days estimate? It will depend on the engineer, and whether this task has been done before or not? If it is a routine task, and has been performed many times, a single point estimate may be ok
But if it is something never done, or is a new activity, or the engineer is new to this activity, this number may well be incorrect. In such cases, going for a three point estimate will give you more reliability

## Slide 39: Example-1:
Manager: Usually how long does it take to complete the engine design?
Engineer: About 5 days.
Manager: Great. And what if there were problems… unexpected issues come up, and there are new things that we haven’t thought up of arise?
Engineer: Well, in that case, it might take as long as 10 days, worst case!
Manager: I see. And how about if everything goes smoothly. No hiccups, and no problems? What’s the best case?
Engineer: Then I could get it done in just 3 days flat.

## Slide 40: Example-2
Let us assume that we have to estimate how much time it will take to go from our home to our work place, we can think of 3 different conditions:
Optimistic – Roads would be free of any traffic congestions and we will not encounter and Red signals (45 min)
Pessimistic – There might be serious traffic bottlenecks like a major accident on the road and our vehicle may breakdown (225 min)
Most Likely – There would be regular traffic conditions (90 min)

## Slide 41: PERT vs Triangular
Estimators typically are capable of providing a more confident guess for the Mode than they are for the Minimum or Maximum.
For example, if you are asked “What is the maximum time required for this activity?” your mind can race with possibilities of what could go wrong, making it difficult to give a definitive maximum.
Though both distributions require “three point” estimates, the PERT formula relies less on the minimums and/or maximums in order to arrive at a prudent (risk adjusted) “expected” value.