## Slide 1: Software Project Management
Controlling Process Group
(Earned Value Management)

## Slide 2: Measure Performance
You need to measure performance so that you can quantify whether or not your project is progressing as expected.

## Slide 3: Earned Value Management
Earned Value Management (EVM) is a way of measuring your performance (and the performance of your project team) at any given date or point in the schedule.
The basic premise of EVM is that the value of a piece of work is equal to the amount of funds budgeted to complete it.

## Slide 4: Earned Value Management
You compare your projected progress with your actual progress on a certain date.
By evaluating the status of your project costs and schedule.
Your communication plans should define how your performance measurements are reported and how often you need to create and distribute that information.

## Slide 5: Earned Value Formulas
Budgeted at Completion (BAC) This refers to the amount that you planned for the cost of the project.
Planned Value (PV) Planned value refers to how much you planned for particular activities to cost during a certain stretch of time.
Actual Cost (AC) Actual cost refers to how much the project work actually costs as of a certain date.
Earned Value (EV) Value of this project work as of this particular date or particular point in the schedule

## Slide 6: Earned Value Formulas
Budgeted at Completion (BAC) This refers to the amount that you planned as the total cost of particular activities.
Planned Value (PV) Planned value refers to how much you planned for particular activities to cost during a certain stretch of time. Planned percentage complete × the amount Budgeted at Completion (BAC)
Actual Cost (AC) Actual cost refers to how much the project work actually costs as of a certain date. Indirect costs + Direct costs
Earned Value (EV) Value of this project work as of this particular date or particular point in the schedule Actual percentage complete × the amount Budgeted at Completion (BAC)

## Slide 7: Calculating PV
How much did you plan to have completed at this point in time?
Your percentages may vary, but for our example, we say that you planned on having 25 percent of the code completed by June 29. But you’ve actually completed just 20 percent
You had planned on your project having a value of $30,000 at this point in time.

## Slide 8: Calculating EV
How much work your team completed at a particular point in time?
Just take the actual percent of the project that your team has completed and multiply by how much you said you would spend for the entire project.
At this point in time, your project has an earned value of $24,000.

## Slide 9: Point to think:
Because you planned on your project having a value of $30,000 at this point in time, but it only has a value of $24,000, you have a $6,000 variance

## Slide 10: Calculating AC
You add your direct costs to your indirect costs to determine your Actual Cost.
  Direct Costs: Include all monies spent directly for your software project.
  Indirect Costs: Refer to monies spent on resources or other items that may be shared among several projects, such as overhead.
Consider or Assume: AC= Rs.35,000

## Slide 11: Direct Vs Indirect Cost:
Direct Cost:
Direct costs are expenses a company can easily connect to a specific object, or cost object. Companies describe these as expenses where you get what you pay
e.g.
  Salaries are wages (including vacations, holidays, sick leave, and other excused absences of employees working specifically on objectives of a grant or contract – i.e, direct labor costs).
  Other employee fringe benefits allocable on direct labor employees.
  Consultant services contracted to accomplish specific grant/contract objectives.

## Slide 12: Direct Vs Indirect Cost:
Indirect Cost:
Indirect costs are expenses that affect the company as a whole and not just the product. Quite often, these are referred to as the real costs of doing business.
e.g.
  Salaries of administrative and clerical staff providing normal support activities in the department, college or school
  Office supplies including postage
  Local telephone calls
  Memberships etc

## Slide 13: Using PV, AC & EV
You know whether or not you are ahead of or behind the planned schedule
You know whether your costs are more or less
You can plan for what changes you need to make for the rest of the project
Report your progress to your sponsor and stakeholders

## Slide 14: Performance Indexes
An index indicates how efficiently your project is progressing and may be used to predict your project’s future performance.
  Cost Performance Index (CPI) CPI = EV / AC = 30,000 / 35,000 = 0.86
  Schedule Performance Index (SPI) SPI = EV / PV = 30,000 / 45,000 = 0.67

## Slide 15: Estimate at Completion (EAC)
What do you expect the total value of the project will be when all the work activities of the project are completed?
EAC is amount of work you estimate it will take to complete the scheduled activities?
You use the EAC to forecast the total value considering how efficiently you are completing project activities.

## Slide 16: Estimate at Completion (EAC)
You must take into account two things when determining your EAC: your BAC and your CPI (Cost Performance Index). EAC = BAC / CPI For Example: EAC = Rs. 100,000 / 0.86 = Rs. 116,279 NOTE: Your CPI tells you how much you are getting for every dollar you spend

## Slide 17: Estimate to Complete (ETC)
How much more you should expect to spend for the rest of the project activities based on your performance thus far.

## Slide 18: Estimate to Complete (ETC)
How much more you should expect to spend for the rest of the project activities based on your performance thus far. ETC = EAC – AC ETC = Rs. 116,279 – Rs.35,000 = Rs. 81,279

## Slide 19: Variance
You use variance analysis to start figuring out if your variance is significant, what the reason for the variance is, and what, if anything, you should do about it.

## Slide 20: Variance Formulas
Cost Variance (CV) What’s the difference between what you planned to spend and how much did you actually spend
Schedule Variance (SV) What’s the difference between your planned schedule and where are you in your schedule
Variance at Completion (VAC) VAC is the difference between what you budgeted to spend when you documented your original project plan and how much you expect to spend by the time you complete your project.

## Slide 21: Variance Formulas
Cost Variance (CV) What’s the difference between what you planned to spend and how much did you actually spend CV = EV – AC = Rs.30,000 – Rs.35,000 = -Rs.5,000
Schedule Variance (SV) What’s the difference between your planned schedule and where are you in your schedule SV = EV – PV = Rs.30,000 – Rs.45,000 = -Rs.15,000
Variance at Completion (VAC) VAC is the difference between what you budgeted to spend when you documented your original project plan and how much you expect to spend by the time you complete your project. VAC = BAC – EAC = Rs.100,000 – Rs.116,279 = –Rs.16,279

## Slide 22: Earned Value Management
BAC = Budgeted at Completion
Planned Value (PV) = Planned %age Complete X BAC
Actual Cost (AC) = Indirect costs + Direct costs + All other costs
Earned Value (EV) = Actual %age Complete X BAC
Cost Performance Index (CPI) = EV / AC
Schedule Performance Index (SPI) = EV / PV
Estimate at Completion (EAC) = BAC / CPI
Estimate to Complete (ETC) = EAC – AC
Cost Variance (CV) = EV – AC
Schedule Variance (SV) = EV – PV
Variance at Completion (VAC) = BAC – EAC

## Slide 23
Q & A